## 00_Read_me
Field | Value
Document | reloved Phase 1 — client status pack
Date | 9 September 2026
Live site | https://reloved-digital.web.app
Domain | reloved.digital — not yet connected to the live site
How to use | Share tabs 01 to 05. Keep language simple. Launch left is Tab 02. Deeper logistics are Tab 03.
Bottom line | Site is live. About 1–2 days of Totem work to close launch cleanly. Full Borzo and hidden numbers are Phase 2.

## 01_Done
Status | Area | What was delivered | In plain words
Done | Phase 1 — Brand | Logo, colours, fonts, and site look | The brand look is live across the site
Done | Phase 1 — Website | Home, Wall of Kindness, item pages, Wall of Love, map, Our Story, policies, contact | All main public pages work
Done | Phase 1 — Give | Photo-first give flow with upload and tracking | Someone can give an item end to end
Done | Phase 1 — Claim | Claim an item with tracking reference | Someone can claim from the Wall
Done | Phase 1 — Partners & contact | Partner application and contact forms | Enquiries and partner applications work
Done | Phase 1 — Sign-in | Email and phone one-time code login | People can sign in securely
Done | Phase 1 — Emails | Emails for submissions, confirmations, and status updates | Donors and claimants get notified
Done | Phase 1 — Admin | Admin can review, approve, or decline items | Your team can run the pilot day to day
Done | Phase 1 — Search & analytics | Basic search setup and visitor analytics | You can see traffic and search basics
Done | Phase 1 — Live site | Working live website | Live at https://reloved-digital.web.app
Done | Extra (beyond original plan) | Google Sign-In | One-tap Google login added
Done | Extra (beyond original plan) | Smarter accounts | Email and phone login stay the same person
Done | Extra (beyond original plan) | FAQ page | Common questions answered on the site
Done | Extra (beyond original plan) | Help widget | Instant help on the website
Done | Extra (beyond original plan) | Faster admin photo suggestions | Admin gets title/category suggestions from a photo
Done | Extra (beyond original plan) | Approve / decline follow-up emails | People hear back when a decision is made
Done | Extra (beyond original plan) | Giver logistics choices | Receiver collects / I send / porter + who pays
Done | Extra (beyond original plan) | Map building location | Building/locality already captured on the site map
Done | Extra (beyond original plan) | Legal acceptance polish | Clearer Terms and Privacy acceptance

## 02_Left_for_launch
Priority | Status | Task | What this means | Who
Must for launch | Not done | Connect reloved.digital | Make the real domain open the live website | You (DNS) + Totem
Must for launch | Not done | Privacy rule message | Tell donors: bag the item, hand to main gate security, do not share flat/wing | Totem
Must for launch | Not done | Simple pickup divert | Button opens Borzo/porter with building already filled from the map (simple link, not deep system build) | Totem
Must for launch | Not done | Donor “rider on the way” message | SMS checklist when a rider is dispatched (bag, guard, tell courier) | Totem + SMS registration
Must for launch | Not done | Simple partner handoff | For launch: redirect to the selected partner (keep it simple) | Totem
Must for launch | Not done | QR codes | QR for Instagram and the website so people can follow | Totem / Marketing
Must for launch | Not done | Marketing alignment | Site and first “What is Reloved” content ready together | Marketing + Totem
Must for launch | In progress | Production SMS sender name | SMS sender ID RELOVD is submitted and waiting for approval | You / TRAI process + Totem
Nice to have | Not done | Hero copy polish | “DROP SOMETHING. PASS IT ON” and final button styling if anything still looks off | Totem
Nice to have | Not done | How-it-works video | Add the video or remove “coming soon” | You (video) + Totem
Later (not launch) | Not done | Full partner matching | Match a donation to a named NGO and close the handoff in admin | Totem — Phase 2 / deeper build

## 03_Phase2_Later
Phase | Status | Task | What this means | Why later
Phase 2 | Later | Full Borzo integration | Auto-open Borzo, fill all fields, track pickup end to end | Needs Borzo business account and deeper build
Phase 2 | Later | Driver gate-only note | Automated rider note: collect from main gate security, do not call flat | Part of full delivery setup
Phase 2 | Later | Hidden phone numbers | Cloud calling so driver and donor never see each other’s real number | Needs Twilio/Exotel setup and KYC
Phase 2 | Later | Full delivery operations | Missed/failed deliveries, returns, fuller donor–claimer messaging | Needs careful design — agreed not to rush into live product

## 04_Work_calendar
Date | Day | Work happened? | What was going on (simple)
2026-08-12 | Wednesday | Contract | Phase 1 scope signed
2026-08-19 | Wednesday | Yes | Build work started
2026-08-20 | Thursday | Yes | Build continued (original target date for live on main domain)
2026-08-21 | Friday | Yes | Homepage and Wall of Kindness published
2026-08-22 | Saturday | Yes | Login codes and homepage polish
2026-08-23 | Sunday | No | No work logged
2026-08-24 | Monday | Yes | Give flow and item details improvements
2026-08-25 | Tuesday | Yes | Homepage cleanup toward live launch
2026-08-26 | Wednesday | Yes | Map, addresses, donor account, uploads
2026-08-27 | Thursday | Yes | Wall, donor flows, production home polish
2026-08-28 | Friday | No | No work logged
2026-08-29 | Saturday | Yes | End-to-end give/upload and backend checks
2026-08-30 | Sunday | No | No work logged
2026-08-31 | Monday | Yes | Google login, emails, handover package
2026-09-01 | Tuesday | Yes | Data and design polish
2026-09-02 | Wednesday | Yes | Hero, legal pages, emails, mobile Wall fix
2026-09-03 | Thursday | Yes | Mobile checks and final polish before short pause
2026-09-04 | Friday | No | Pause
2026-09-05 | Saturday | No | Pause
2026-09-06 | Sunday | No | Pause
2026-09-07 | Monday | No | Pause
2026-09-08 | Tuesday | Yes | Launch planning, privacy/pickup discussion, SMS sender registration started
2026-09-09 | Wednesday | Yes | Launch vs Phase 2 list finalised with client conversation

## 05_Time_summary
Item | Number | In plain words
Active work days so far | 15 | Days where build or launch work was done (19 Aug – 9 Sep, with a short pause)
Days with no work logged | 7 | 23, 28, 30 Aug and 4–7 Sep
Short pause | 4 days | 4–7 September
Site live today | Yes | https://reloved-digital.web.app
Real domain connected | Not yet | reloved.digital still needs to point to the live site
Estimated Totem days left to close launch | 1–2 days | Domain + privacy message + simple pickup divert + light launch items
If full NGO matching is included now | 6–10 days | Larger feature — can stay for later if launch stays simple
Full Borzo + hidden numbers (Phase 2) | 12–20 days | Separate quote — agreed to do after launch